## Sheet1
Bug Reports
Bug ID | Title | Environment | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | ScreenShort
BR_001 | Forgot Password functionality is missing | Windows 11, Chrome v122, Edge v122 | High | High | 1. Navigate to https://proxify.gg/login 2. Click on the 'Forgot Password' link 3. Observe the response | A password reset email should be sent to the registered email. | The 'Forgot Password' functionality does not exist on the page. | Open | N/A
BR_002 | Social Login with Google is not implemented | Windows 11, Chrome v122, Firefox v118 | Medium | Medium | 1. Navigate to https://proxify.gg/login 2. Click on the 'Login with Google' button 3. Observe the response | User should be redirected to Google authentication and logged in successfully. | The 'Login with Google' button does not perform any action, indicating the feature is not implemented. | Open | N/A
BR_003 | Support and Contact Us links are not working | Windows 11, Chrome v122, Firefox v118 | Low | Low | 1. Navigate to https://proxify.gg/login 2. Click on 'Support' or 'Contact Us' links 3. Observe the response | Users should be redirected to a working support/contact page. | The links do not navigate to any support or contact page. | Open | N/A
BR_004 | Already registered Email but there are not response | Windows 11, Chrome v122, Firefox v118 | LOW | Medium | "1. Open the Proxify sign-up page 2. Enter a valid username 3. Enter an already registered email 4. Enter a valid password 5. Click on reCAPTCHA ""I'm not a robot"" 6. Accept the Terms and Conditions 7. Click on the ""Sign Up"" button" | Error message should appear: "Email already registered" | There are Not response to be exact message. | Open | N/A
BR_005 | User should receive an error message when entering an invalid email | Windows 11, Chrome v122, Firefox v119 | LOw | Medium | "1. Open the Proxify sign-up page 2. Enter a valid username 3. Enter an invalid email format (e.g., userexample.com) 4. Enter a valid password 5. Click on reCAPTCHA ""I'm not a robot"" 6. Accept the Terms and Conditions 7. Click on the ""Sign Up"" button" | Error message should appear: "Invalid email format" | work is correctly but ui not appear to message | Open | N/A
BR_006 | User should receive an error message when entering an excessively long username | Windows 11, Chrome v122, Firefox v120 | High | High | "1. Open the Proxify sign-up page 2. Enter a username with more than the allowed characters (e.g., ThisIsAnExcessivelyLongUsernameBeyondLimit) 3. Enter a valid email ID 4. Enter a valid password 5. Click on reCAPTCHA ""I'm not a robot"" 6. Accept the Terms and Conditions 7. Click on the ""Sign Up"" button" | Error message should appear: "Username exceeds character limit" | There are longest input take it . | Open
BR_007 | User should receive an error message when entering a username with special characters | Windows 11, Chrome v122, Firefox v121 | High | High | "1. Open the Proxify sign-up page 2. Enter a username with special characters (e.g., user@#123) 3. Enter a valid email ID 4. Enter a valid password 5. Click on reCAPTCHA ""I'm not a robot"" 6. Accept the Terms and Conditions 7. Click on the ""Sign Up"" button" | Error message should appear: "Username cannot contain special characters | Any value accepted | Open